## EDI ACTION PLAN
Strategic Objective | Strategic Priority | Key measures of success | Links to: | Actions | Who | When | Progress Update | Progress Update Jan 25 | Progress Update April 25 | Progress Update June 25 | Status
ORGANISATION | We will:
We will make South Yorkshire Safer and Stronger by improving trust and confidence in our services that are inclusive, safe and professional. We will strengthen our leaders to champion our commitment to EDI and celebrate EDI in everything that we do. We will work hard to make this an inclusive and safe place to work, where all our people are valued, supported and able to thrive. | 1. Embed EDI and Positive Action into our Culture Programme | Survey staff to capture confidence levels in EDI There is a measurable understanding across the service of our plans and priorities and performance standards and how each of us contributes to these, using the Personal Review (PR) process to record this Develop an EDI dashboard to report against EDI LPI’s | 23/24 Service Plan - Implement commitments we made to the Fire Authority following London’s independent culture review CcoE Project Benefits FFTF IO7: An inclusive culture is at the heart of every fire and rescue service. They are welcoming and supportive places to work, retaining the widest variety of people from all backgrounds throughout their careers. HMICFRS Recommendation 23 CFO should seek regular feedback from staff about values, culture, fairness and diversity, with due regard to the leading and developing people standard. They should show how they act on this feedback. Culture Survey Action Plan. | OG1a. Support the Culture Survey Action Plan to deliver bespoke sessions to staff groups. | Strategic Influencers, SPP Culture Programme Lead | 2024-12-01 | June 24 - Linda Haigh delivered session to Women's Staff Network Covered in Joint Staff Group 27/06/24. |  | April 25 - complete | June 25 - action completed | Complete | Behind Schedule
|  |  |  | OG1b. Monitor and take action on responses to the EDI question in Pulse Survey | Survey Response Group | Ongoing | Aug 24 - data has been captured and analysis is carried out on an ongoing basis. | Jan 25 - ongoing e.g. action on Neurodiversity picked up and followed up. | April 25 - data reported in EDI Committee 24/04/25 - 4.3% - re understanding what EDI means and why it matters. To be monitored on an ongoing basis. | June 25 - no further update at this time. | On Schedule | Significantly Behind Schedule
|  |  |  | OG1c. Focus on inclusion (through policies and practices) as part of promoting SYFR as employer of choice with regards to recruitment and retention | All, SPP Culture Programme Lead | Duration of Strategy | June 24 - Awaiting Culture Action Plan - which will be ratified at People & Culture board in September 2024. EDI team have been consulted with in relation to the inclusion aspects of the 6 themes in the culture action plan | Jan 25 - updates made to a range of policies and associated documents. Tracked via action log and discussed at team meetings (539285). | April 25 - date to finalise changes to Disability, ND & Workplace Adjustments Policy set. Draft Neonatal and Fertility Policies. Presentation to DCN Staff Group on People Policies that support carers(PowerPoint created). | June 25 - still ongoing - bulletin prepared to update on progress | On Schedule | On Schedule
|  |  |  | OG1d. Ensure EDI Action Plan contains Positive Action objectives | People Partner OD (EDI), PA&E Officer | Annually by 31st October | See below | Jan 25 - Agreed objectives and priorities and have a document to track progress. |  | June 25 - work to commence on plan for 2026 and review of 2025 activities is ongoing | On Schedule | Not yet started
|  |  |  | OG1e. Recruit and set objectives for our PA and Engagement role | People Partner OD (EDI) | 2024-03-01 | June 24 - Interviews taken place June 2024, awaiting outcome. Sept Due to issues in recruiting to role, funds reallocated to a PA Support Officer (PT) and nominal non pay budget. | Jan 25 - completed as part of the probation for the new post holder and tracked in EDI team meetings. | April 25 - complete | June 25 - action completed | Complete | Complete
| 2. Reinforce the embedding of our Equality Impact Assessment process | Survey staff to capture confidence levels in equality, diversity and inclusion Numbers of staff undertaking mandated and supplementary training More frequent and impactful consultation | HMICFRS Recommendation 27: CFO should make sure their equality impact assessments are fit for purpose and, as a minimum, meet the requirements of the NFCC SHOAL action AC214QMNNJ 2024 Service Action Plan | OG2a. Establish connections with peers to carry out assessments on EqIAs | People Partner OD (EDI) & EDI Advisor (JCSD) | Originally 01/03/2024 changed to 31/12/25 | June 24 - offered made - individuals left role - new contacts required. | Jan 25 - policy & process updated to enable greater internal governance. Introduction of new EqIA inbox and changes made to CMB report template and list of EqIAs being maintained, communication via bulletin regarding these updates. | Apr 25 - this will be a focus of the next round of communication now the EDI inbox has been established. Review of completion date carried out - changed to Dec 25. Focus will be on assessing the quality of completed EqIAs. | June 25 - no further update at this time. | On Schedule | Complete - move to BAU
|  |  |  | OG2b. Consider how to collate all EqIAs in a central point |  | 2024-06-01 | June 24 - Request made to Governance manager for consideration in new Risk Management system | Jan 25 - Action no longer valid - replaced by introduction of EqIA inbox see OG2a above. | Complete | June 25 - action completed | Complete
|  |  |  | OG2c. Record when consultation is carried out on EqIAs |  | Ongoing | June 24 - Records as kept as we are notified - further work to determine departmental processes | Jan 25 - spreadsheet created that logs when an EqIA has come into the inbox for consultation. Project Team log all EqIAs and their review as part of standard project documentation. | April 25 - complete | June 25 - action completed | Complete - move to BAU
|  |  |  | OG2d. Monitor the number of consultations carried out on EqIAs |  |  |  | Jan 25 - as per OG2c. | April 25 - complete | June 25 - action completed | Complete - move to BAU
|  |  |  | OG2e. Monitor the number of staff undertaking EqIA training |  |  | June 24 - Registers and attendance maintained | Jan 25 - Regular bulletins reminding of the dates for the training. Content updated in line with updates to policy & guidelines. | April 25 - complete | June 25 - action completed | Complete - move to BAU
|  |  |  | OG2f. Evaluate / monitor the quality of EqIA training |  |  | June 24 - Feedback form created | Jan 25 - evaluation being collected. | Ongoing | June 25 - ongoing - had to postpone the session in June - bulletin with dates for 2026 to be shared soon. | On Schedule
| 3. Consider EDI within SYFR infrastructure and facilities developments | Monitoring feedback from training provided Demonstrable appropriate EDI actions implemented at all stages of infrastructure and facilities developments |  | OG3a. Joint production of a template for refurbishments / new builds that incorporates EDI. | People Partner OD (EDI), EDI Advisor (JCSD) & Estates Project Manager | 2025-12-01 | June 24 - To schedule workshop to set “benchmarks” following staff group review of the multi-faith rooms | Jan 25 - work ongoing across all staff groups to review multi-faith provision - including specification for each room. | Ongoing | June 25 - action ongoing - will be update at JSG on 3rd July. Monthly meetings scheduled with estates team - work being led by Faith & Belief staff group. | On Schedule
|  |  |  | OG3b. Consultation with key groups on refurbishments / new builds |  | Ongoing | June 24 - Taking place regularly e.g. Elm Lane, Maltby EDI Phase 1, TDC Instructor Showers | Jan 25 - see OG3a. | April 25 - work is ongoing for the Elm Lane refurbishment. EqIA has been consulted on via staff groups and will be reviewed as part of the project. | June 25 - action ongoing | On Schedule
|  |  |  | OG3c. Feedback from end users on refurbishments / new builds |  | Ongoing | June 24 - to be provided by corporate comms. | Jan 25 - updates to be provided via EDI Committee as per the schedule for EDI updates. | April 25 - ongoing as per OG3a & 3b. | June 25 - action ongoing as per OG3a & 3b. | Complete - move to BAU
| 4. Provide mandated and supplementary training and development focussing on EDI | Number of staff completing EDI training / activity / intervention Monitoring feedback from training provided EDI dashboard to report EDI LPI’s | FFTF IO5: Fire and rescue services refocus their investment in the selection, training and development of employees to maintain, support and improve their skills and knowledge throughout their careers. | OG4a. Produce and communicate a library of accessible EDI training resources | People Partner OD (EDI) & EDI Advisor (JCSD) | In line with Annual EDI Report (LPI) As and when training interventions occur. | June 24 - Positive Action & Community Engagement (PACE) guidance distributed April 2024. | Jan 25 - bulletin reminder re training options available. Regular updates regarding dates for EDI training and any new voluntary LearnPro modules or content as part of EDI Calendar of events. Task identified to monitor completion rates and areas for voluntary modules (mandatory ones are subject to review via LPI). Regular feed back provided on one day mandatory EDI training - captured in EDI Update for EDI Committee. | April 25 - Review underway to look at the effectiveness of the current 1 day EDI externally provided training course to determine if any gaps in provision of key skills. | June 25 - action ongoing | On Schedule
|  |  |  | OG4b. Develop dashboard of EDI activity / interventions |  |  | July 24 - will link to data from PACE - development work ongoing. | Jan 25 - PACE up and running but not yet in dashboard format. Includes input from JCSD. | April 25 - meetings underway to determine the governance around PACE data and any reporting lines as well as the level and format of the data required. | June 25 - action ongoing | On Schedule
| 5. Ensure our leaders visibly and effectively champion our commitment to EDI | There is a measurable understanding across the service of our plans and priorities and performance standards and how each of us contributes to these, using the Personal Review (PR) process to record this Having a strategic lead for all staff groups / networks Demonstrable appropriate EDI actions implemented at all stages of infrastructure and facilities developments | FFTF IO8: Political leaders and managers work together to deliver strong inclusive leadership across all fire and rescue services. Common approaches and leadership frameworks will be developed that set out service values, expectations and behaviours which all can support and promote. This will be the basis on which fire and rescue services are led and all employees operate. Culture Action Plan 1.9: Work with Staff Groups to support delivery of identified priorities 4.1: Develop mechanism to increase stakeholder involvement in equipment testing/purchase and communicate feedback on procurement decisions 4.2: Work through appropriate committees / stakeholder groups to develop and communicate a programme of upcoming capital works (to include prioritisation criteria, scope of works, timescales, and named contacts from both Estates and business area). Annual Service Plan for 2023/24 - In 2023/24 we will: • Identity and implement better support for neurodiverse staff and those with disabilities • Further empower staff networks to help us drive workplace improvements | OG5a. Incorporate EDI actions into function and station plans | All | Ongoing | July 24 - awaiting confirmation from districts regarding this. | Jan 25 - evidence in PACE shows that this is occurring. Task to monitor delivery against objectives and improve communications between districts and EDI team for better planning and positive PA initiatives. | April 25 - meeting taken place to improve links between districts and EDI team to ensure appropriate support for organising and evaluation events takes place. Communication in draft. | June 25 - action ongoing | On Schedule
|  |  |  | OG5b. Ensure the intranet EDI content is accessible and informative | People Partner OD (EDI), EDI Advisor (JCSD), Staff Groups | 2024-06-01 | July 24 - review ongoing by EDI team. | Jan 25 - updates made to all pages - will be ongoing work to look to improve content and include more input from staff groups. | April 25 - complete | June 25 - action completed | Complete - move to BAU
|  |  |  | OG5c. Influence the content of corporate inductions to incorporate relevant EDI content |  | 2024-04-01 | April 24 - content added - to be review ongoing by EDI team. | Jan 25 - EDI Handbook utilised as part of induction from Autumn 24. | April 25 - complete | June 25 - action completed | Complete
|  |  |  | OG5d. Develop our leaders understanding of EDI related aspects. |  | Ongoing | July 24 - To be included in the review of all EDI related training documents, EDI objectives & use of additional skill booster modules. Strategic Influencer (SI) nominated for each staff group / network. | Jan 25 - additional skill booster modules added. Included as part of planning for EDI Calendar. Staff Handbook and Toolkit provided and updated and awareness provided on specific subjects at MM. EDI KPI data demonstrates that the 1 day training shows an increase in knowledge - pre and post course. Review of SI carried out - request made to groups/network to assess if want to change / rotate SI. | April 25 - request for regular slot at MM for EDI related content (dates 09/07, 24/09, 17/12/25 - to include Neurodiversity & Positive Action). | June 25 - action ongoing - to agree order of content at JSG on 3rd July 2025. | On Schedule
|  |  |  | OG5e. Encourage and facilitate involvement in staff groups |  | Ongoing | July 24 - work ongoing with staff group chairs regarding this - link to JSG and SEF, corporate comms inclusion work and regular comms from EDI team. | Jan 25 - membership levels increasing for staff groups. Regular bulletins circulated re staff groups. Staff groups invited to take part in corporate inductions. Support given via Staff Group Toolkit and Handbook as well as use of CPD element in Staff Engagement Forum / Joint Staff Groups 13/02/24 - review staff group guidance re attending events as well as staff group meetings. LH raise at function meeting re how this supports service priorities | April - work ongoing to develop CPD element for next Staff Engagement Forum on 26th June. | June 25 - action ongoing - allyship covered for June SEF meeting. Also on agenda for JSG on 3rd July. | On Schedule
| 6. Encourage our people to have a voice, contribute and offer constructive challenge, through a variety of channels | Survey staff to capture confidence levels in EDI Development of a dashboard that reports against EDI LPIs | HMICFRS Recommendation 28: CFO should review how they gather and use equality and diversity data to improve their understanding of their staff demographics, including applying and meeting the requirements of the NFCC equality, diversity and inclusion data toolkit. Culture Survey Action Plan - 1.7 Focus on ally ship, developing communications and identifying supporting development ally ship, developing communications and identifying supporting development | OG6a. Identify channels for individuals to comfortably have a voice | Senior People Partner (OD) People Partner OD (EDI) | 2024-06-01 | Jun 24 - Channels identified - will form part of SYFR culture action plan (Theme 1 - build an inclusive workplace - due dates between Sep & Oct 24). | Jan 25 - Standard bulletin re comms re monitoring data sent out. | April 25 - work ongoing to review the categories on our EDI monitoring form. | June 25 - action ongoing - is a priority area to enable work to be carried out for recrutiment team to log data in line with monitoring requirements. Due date for action to be revised from June 24. | On Schedule
|  |  |  | OG6b. Review LPIs utilising the Orca dashboard |  | 2024-02-01 | March 24 - review carried out - further work needed around capturing date - to be reviewed later in 2024. | July 24 - issues with LPIs - draft dashboard created - further work required before can incorporate additional LPI areas. Jan 25 - meeting arranged during Feb 25 to begin the review of the LPIs and their accessibility / accuracy. | April 25 - ongoing - will require a review of the due date. | June 25 - action ongoing. Will form part of wider departmental work on function Local performance Indicators and supporting team Key Performance Indicators. Some improvemnts made to current data available in ORCA but still subject to review and updates. | Behind Schedule
|  |  |  | OG6c. Increase Pulse Survey participation |  | 2024-12-01 | Aug 24- Will be a measure in the analysis of the Pulse Survey | Dec 24 - this work will be classed as ongoing. This forms part of the work of the working group responsible for analysing response rates and comments from all pulse surveys. | April 25 - EDI related question responses being monitored. | June 25 - action ongoing | on schedule
|  |  |  | OG6d. Provide support for Staff Engagement Forum & Staff Groups |  | . | June 24 - support provided by secretariat. | Jan 25 - this is provided on an ongoing bias in relation to setting and reviewing objectives & EDI Action Plan. | April 25 - completed | June 25 - action completed | Complete - move to BAU
|  |  |  | OG6e. Encourage and facilitate involvement in staff groups |  | Ongoing | July 24 - work ongoing with staff group chairs regarding this - link to JSG and SEF, corporate comms inclusion work and regular comms from EDI team. | Dec 24 - is standard agenda item on the Joint Staff group agenda and the Staff Engagement Forum template. | April 25 - completed | June 25 - action completed | Complete - move to BAU
| 7. Share best practice in regional and national EDI forums | Involvement in key external groups, bodies and partnerships | NFCC Positive Practice Portal FFTF IO9: Fire and rescue services have access to comprehensive national implementation support and a repository of standards, guidance and tools that they embed in their own local service delivery. | OG7a. Contribute to consultation for NFCC on toolkits and best practice documents | Senior People Partner (OD) People Partner OD (EDI) & Staff Groups | Ongoing | Neurodiversity Handbook added to NFCC PP portal August 24. | Jan 25 - this is ongoing as part of the work of the function. Review carried out in managers meeting to keep all updated on ongoing consultation and to nominate relevant participants. Recent ones include Culture Symposium. New for 2025 is involvement in Anti-racism recruitment processes working group with Doncaser and Bassetlaw Teachng Hospitals NHS Foundation Trust. | April 25 - EDI team invited to NFCC event Talking About Race (13:00 – 15:00, 1 May 2025) ahead of the NFCC Racial Equality Toolkit launch. EDI Team provided guidance to another FRS on our approach to neurodiversity (after seeing the work on the positive practice portal). | June 25 - action ongoing - meeting planned to review content of the NFCC Anti Racism Toolkit and SYFRs Anti Racism Toolkit to establish how this will be incorporated into our work. | On Schedule
|  |  |  | OG7b. Utilise the NFCC Positive Practice Portal | People Function |  | June 24 - Neurodiversity Handbook added to portal. | Jan 25 - review of content on portal ongoing to establish if best practice to be adopted. | April 25 - completed | June 25 - action completed | Complete
|  |  |  | OG7c. Play an active role in groups and forums to bring best practice into SYFR |  |  | July 24 - links made with NFCC contacts | Jan 25 - this will happen on an ongoing basis across the People Function. | April 25 - links to OG7a above. Recent attendance at NFCC PL Hub 23/04/25 (People, Culture and Leadership). | June 25 - action ongoing | On Schedule
| 8. Improve availability and analysis of EDI information and statistics | Development of a dashboard that reports against EDI LPIs | NFCC Data - check new Data Portal - HMICFRS Recommendation 29 - By 1 December 2023, the Home Office should publish greater detail on the PC data it collects about FRS staff, including joiners and leavers, by rank and role. Not our responsibility but could refer to this data - comparisons in WFD Profile? 23/24 Service Plan - Improve staff understanding of Orca and the ways it can support their work | OG8a. Update Internet to make EDI information more accessible, detailed and representative. | People Partner OD (EDI), EDI Advisor (JCSD) & Staff Groups | 2024-11-01 | Jul 24 - task allocated to EDI team - is being monitored now and recommendations for changes being made and implemented. | Nov 24 - all intranet pages updated. Task added as recurring event in EDI team diary. | April 25 - complete | June 25 - action completed | Complete - move to BAU
|  |  |  | OG8b. Review reporting, content, feedback and layout for EDI related documents |  |  | Aug 24 - list of policies compiled and work ongoing to check if updated version is available and schedule for updating added to calendar for EDI team. | Jan 25 - request from CMB to add more detail to data in WFDP and EDI Annual Report for 2024. To consider how to incorporate this additional data in reports for 2025. | April 25 - complete | June 25 - action completed | Complete - move to BAU
PEOPLE | We will:
SYFR will be a leading fire and rescue service that is able to attract, recruit and retain a diverse workforce Create the right culture, values and behaviours to make this a brilliant place to work that is inclusive for all | 1. Embed a comprehensive education programme to provide knowledge and understanding of EDI | Complete the 3 year roll out plan of mandated EDI training | FFTF IO6: Prospective employees are attracted to fire and rescue services as an employer of choice where inclusive recruitment practices and the available diverse roles and responsibilities help the service manage risk in the local community. | PE1a. Monitoring of completion / satisfaction of EDI training | Senior People Partner (OD) People Partner OD (EDI), EDI Advisor (JCSD) & Staff Groups | Ongoing | Sept 24 - is agreed LPI and included in EDI Annual Report. Further work identified to check if additional areas of training required by those attending initial 1 day external course. | Jan 25 - monitoring of additional voluntary LearnPro modules carried out. Ongoing need to ensure feedback gained from all EDI courses. Look at utilising additional features in Microsoft 365 to facilitate this. | April 25 - EDI Training evaluation questions added. To be reviewed and added into MS Forms then circulated. | June 25 - action ongoing | On Schedule
|  |  |  | PE1b. Deliver a programme of education and development around EDI |  |  | Aug 24 - will link into task above once evaluation carried out regarding training needs in relation to EDI following on day external training. | Dec 24 - sent bulletin reminding all of the EDI training options available. | April 25 - will depend on the outcome from PE1a. | June 25 - action ongoing - will depend on the outcome from PE1a. | On Schedule
|  |  |  | PE1c. Deliver fair recruitment training for all involved in recruitment / promotions | People Function | 2025-04-01 | Sept 24 - this is happening on a prioritised / ad hoc basis will be included in bid to WFP committee. | Jan 25 - Ad hoc training till happening. Will form key part of the new recruitment People Partner role. | April 25 - ongoing. | June 25 - action ongoing | On Schedule
|  |  |  | PE1d. Obtain and evaluate feedback on why people join SYFR. |  |  | Sept 24 - data captured on application form and recorded on recruitment spreadsheet. Carried out a review of job board providers - to be revisited in Q1 2025. | Jan 25 - subject to ongoing review. | April 25 - work not yet completed - to change status to behind schedule. | June 25 - action ongoing - status changed to behind schedule in April 25. | Behind Schedule
| 2. Embed inclusive language in policies, procedures and guidance documents | Review and refresh policies and associated literature including the new Application Tracking System (ATS) and recruitment process to encourage the best talent to apply for roles |  | PE2a. Review our policies to ensure they are accessible | People Partner OD (EDI), Staff Groups, People Partner Policy, EDI Advisor (JCSD) | Ongoing | Aug 24 - links to 8b above. Guidance issued by People Function | Jan 25 - People Policy Development guidance and Accessibility guidance drafted to support improvements around accessibility of all policies. | April 25 - Links to OG1c above. Will be part of role for PP responsible for Policies once review of roles & responsibilities carried out. | June 25 - action ongoing. Supported by new Policy Matrix and updates to Policy Tracker on UBIK. | On Schedule
|  |  |  | PE2b. Work with the Recruitment Team in the development of the ATS system |  |  | Aug 24 - on hold | Jan 25 - ATS system no longer progressing - out of contract. Work will need to be carried out to look at how we can make our process more accessible. Will require a review of the action and agreement of future actions in this area. Further work around this will be considered with the introduction of Microsoft 365 to improve the accessibility around finding documents and consideration of best way to index them. | April 25 - work ongoing to review EDI categories used in monitoring and the use of the Disability Confident scheme (previously known as two ticks or guaranteed interview scheme). Will be supported with the development of a new Webpage. Work between Corporate Communications & Recruitment will review the accessibility of our recruitment information. Will be led by the findings from research on barriers commissioned by our corporate communications team. Need to review the status of this task - TO BE CONFIRMED as may need to reword the action. | June 25 - work required to review this action due to the expirty for the licence for the ATS and the recent introduction of Microsoft 365 and how this can support the accessibility of what we do. | Not yet started
| 3. Adopt creative and innovative process to attract diversity | Review and refresh policies and associated literature including the new Application Tracking System (ATS) and recruitment process to encourage the best talent to apply for roles Goals are achieved or exceeded and we see improvements in diversity in recruitment and in progression opportunities |  | PE3a. Review CAD system to repurpose data capture. | People Partner OD (EDI), EDI Advisor (JCSD) | 2024-05-01 | May 24 - completed - further work required to review data captured in PACE. | Jan 25 - PACE being utilised. | April 25 - whilst the original task is complete further work is now required. Meeting taken place to review the responsibility, location, requirements and governance arrangements of PACE data. |  | Complete
|  |  |  | PE3b. Recruit a Positive Action focussed People Partner. Set objectives for delivery of the Positive Action plan |  |  | Aug 24 - completed | Oct 25 - subject to delays, staff changes and re prioritisation of budget. As at Oct 24 - additional role of 2 days per week with focus on positive action. | April 25 - work is progressing in this area and activities have been planned up until June 25 (prior to wholetime recruitment). Evaluation of activities to date to take place to determine any changes needed prior to planning for remainder of 25 and 26. | June 25 - action completed | Complete
| 4. Further empower all staff groups to help us drive workplace improvements | Positive feedback from all staff groups and joint staff group Continued growth and success of employee engagement through our staff groups, surveys, watch & team visits | 23/24 Service Plan - Further empower staff networks to help us drive workplace improvements Audit for 2024 - actions in place to empower staff networks | PE4a. Work with staff group chairs to agree objectives | People Partner OD (EDI) | Ongoing | Aug 24 - ongoing - will be a review / discussion at JSG in December | Dec 24 - standard agenda item for each JSG. Ongoing support from PPOD EDI to use the staff group guidance and framework for objectives | April 25 - this work is ongoing. Staff Group Guidance document is up for review. | June 25 - this action takes place on an annual basis with refular review- status changed from on schedule to completed. | Complete
|  |  |  | PE4b. Offer CPD for staff group members |  |  | Sept 24 - need to agree next CPD topic. | Jan 25 - Discussed at Dec JSG and at Jan SEF. Topic areas shared - work to commence on providing suitable learning for each area. | April 25 - CPD elements of the Staff Engagement Forum Meetings is yet to be finalised prior to next meeting on 26/06/25. | June 25 - action ongoing. Allyship covered in June SEF - subject to further discussion at JSG on 3rd July. | Behind Schedule
|  |  |  | PE4c. Produce an Annual staff group report capturing key outcomes |  | Annually | Aug 24 - work not yet progressed - will depend on data submitted to SEF and to JSGs | Dec 24 - suggestion of annual report discussed at JSG - agreed in principle | April 25 - not yet started | June 25 - to be looked at following JSG on 3rd July | not yet started
|  |  |  | PE4d. Hold Bi annual Joint Staff Groups / Staff Engagement Forums |  | Twice a year | June 24 - booked for 2024 - dates for 2025 to be published. | Dec 24 - agreed standard agendas for both meetings - classed as business as usual. | April 25 - complete | June 25 - action completed | Complete - move to BAU
| 5. Set realistic goals and measures for EDI and Positive Action initiatives to be delivered by all areas of the service | Goals are achieved or exceeded and we see improvements in diversity in recruitment and in progression opportunities Positive results when monitoring and reporting on SYFR diversity profile SMART objectives within the PR system set and achieved | 23/24 Service Plan - Set realistic goals for positive action initiatives across all recruitment areas | PE5. Develop a schedule of annual PA activities - facilitated by a range of staff | People Partner OD (EDI) | Annually | Aug 24 - is a key task for new PA role once in post. | Dec 24 - some delay in developing this due to delay in recruitment (see 3b above) | April 25 - activities planned until June 25. Further work required to plan for remainder of 25 and 26 | June 25 - action ongoing | On Schedule
|  |  |  | PE5b. Review and monitor against EDI LPIs | People Partner OD (EDI) & Snr People Partner | Ongoing | Sept 24 - captured in 2024 Annual EDI Report - to be reviewed for 2025 report to include agreed new areas. | Dec 24 - review of statistics in WFDP shows increase in all monitored protected characteristics. Key role of new PA Officer is around evaluation and assessing the impact of PA activity. | April 25 - whilst the initial tasks is complete, a review of the LPIs/ EDI Dashboard is ongoing. Presented at EDI Committee 24/05/25. Feedback to be use to review content / format of dashboard. | June 25 - action completed | Complete
|  |  |  | PE5c. Produce guidance document on EDI objectives for inclusion in future PR process | People Partner OD (EDI), People Partner (Workforce Planning, Resourcing and Systems) | 2024-12-01 | Aug 24 - completed in draft as part of PR revamp - will look at how this can and should be communicated with more detail that can fit into PR system. |  | April 25 - complete | June 25 - action completed | Complete
| 6. Improve the accountability for effective Equality Impact Assessments to allow for greater monitoring and outcomes | Internal and external scrutiny of EqIA's identifies improvements in quality, impact and delivery of outcomes | HMIC Recommendation 27 - By 1 June 2023 CFOs should make sure their equality impact assessments are fit for purpose (meet requirement in NFCC EQIA toolkit). | PE6a. Provide training and support. Develop records for monitoring of consultations / engagement of EqIA process. | People Partner OD (EDI), EDI Advisor (JCSD) | 2025-01-01 | Aug 24 - new EqIA inbox created. To produce comms to explain to all how this will work. | Dec 24 - task completed - however future work required to look at external involvement in EqiAs. | April 25 - complete | June 25 - action completed | Complete
| 7. Improve awareness across the service of disability in the workplace, particularly neurodiversity, and review and improve support provided | Positive feedback from all staff groups and joint staff group Positive results when monitoring and reporting on SYFR diversity profile Increase in declaration of disabilities and evidence that staff are being supported appropriately | 23/24 Service Plan - Identity and implement better support for neurodiverse staff and those with disabilities RSM Audit Action No. 2 - suggested completion date is December 2025 | PE7a. Introduce RA process to allow self declaration and proactive support provided | People Partner OD (EDI) & Staff Group & Wellbeing | December 2024 | July 24 - ongoing as part of work with People Function led task group. Initial scope for system drafted to be discussed at next meeting on 16th September 24. | Sept 24 - project work ongoing - subject to prioritisation from ICT. This will mean a delay in completing this task. May require a review of the allocated timescale. In the interim a draft Reasonable Adjustments has been consulted upon and will be introduced once further updates complete. Annual bulletin around monitoring data will be sent in Jan & Feb 25. | April 25 - Workplace Adjustments Policy in draft and has been consulted on (staff groups only at this o point). Draft policy to be reviewed 28/04/28 and will then be shared for wider consultation. This will require a review of the completion date for this task - not yet done. | June 25 - action ongoing | Behind Schedule
|  |  |  | PE7b. Develop Neurodiversity Policy (update our Disability Policy) |  |  | Aug 24 - completed in draft. | Dec 24 - both policies (review of disability policy & new neurodiversity policy) subject to ongoing consultation. Due to delay in beginning consultation - completion date to be reviewed. | April 25 - as per PE7a. | June 25 - action ongoing - all updates incorporated and will be presented for next stage of consultation. Final completion date likely to be Autumn 2025. | On Schedule
| 8. Identify gaps in knowledge and prepare guidance/toolkits to support EDI knowledge growth and initiating delivery | Continued growth and success of employee engagement through our staff groups, surveys, Watch & team visits | RSM Audit Action No. 7 - suggested completion date is December 2025 | PE8a. Work with Snr PP to implement casework recommendations | People Partner OD (EDI), EDI Advisor (JCSD) | Ongoing | Aug 24 - ongoing as needed. | Sept 24 - additional guidance around completing EqIAs published. Additional optional LearnPro modules published. To review longer term feedback fro 1 day EDI training to assess any gaps that have been identified in organisational knowledge of EqIAs. | April 25 - as per PE1a. | June 25 - action ongoing | On Schedule
|  |  |  | PE8b. Respond to knowledge gaps with coms, education and guidance development |  |  | Aug 24 - links to 6a above. | Sept 24 - forms part of the EDI calendar of activity. | April 25- links to OG4a. | June 25 - Focus of work between EDI and corporate comunicaitons agreed. Once outlined, to agree a completion date. | Not yet started
| 9. Develop LPIs which allow for worthwhile data and transparency which align with strategic plans | New strategy communicated to all staff and aims understood, evidenced by the pulse survey |  | PE9. Awareness of best practice to understand our gaps - use Maturity Model for gap analysis? | People Partner OD (EDI), EDI Advisor (JCSD) | March 2024 | Mar 24 - gap analysis completed. New task required to consider work required to fill gaps. | Dec 24 - work to commence in Q1 2025 to review LPIs for 2025. Links to OG6b. | April 25 - work not yet commenced. Links to PE5b. | June 25 - action ongoing. New NFCC Anti-Racist Toolkit to be reviewed at JSG on 3rd July | Behind Schedule
PARTNERS | We will:
To connect, collaborate and improve our understanding of our diverse communities and their needs to create best practice | 1. Identify partners and community groups to target safety and recruitment messages | Collaborative working with partners Develop a system to allow better data capture of EDI focussed community engagement by SYFR staff |  | PA1a. To be aware of developments within the third party Fire Risk Community Model. | EDI Advisor (JCSD) | 2024-06-01 | Jun 24 - ongoing. |  | April 25 - ongoing. | June 25 - action ongoing | On Schedule
|  |  |  | PA1b. Create and maintain a database of community contacts | People Partner OD (EDI), EDI Advisor (JCSD), Staff Groups |  | Aug 24 - database requires updating once new PA role in place. Will be key task of this role. | Dec 24 - database to be updated on an ongoing basis. Comms to go out early 25 asking all for ideas / suggestions for community contacts. | April 25 - complete |  | Complete - move to BAU
|  | Engagement in EDI and similar events across South Yorkshire Develop a system to allow better data capture of EDI focussed community engagement by SYFR staff | FFTF IO10: Opportunities to collaborate are considered in all aspects of service delivery, where it will bring about better outcomes for communities. Partnership working will be based on solid evidence and data to determine the most efficient and effective use of resources to ensure the safety of the public and our employees. | PA2a. Incorporate EDI activity into function & station plans | Heads of Function | 2024-04-01 | May 24 - EDI team awaiting confirmation of what is incorporated into station plans currently. | Dec 24 - EDI team to attend / share information for/at district meetings. Jan 25 - activities being led by districts and copied into Positive Action Calendar. Links to PACE updates shared Jan 25. | April 25 - subject to discussions with Service Delivery. Communications sent to districts on how to utilise the PACE guidance and toolkit. Confirmation received that PA is incorporated into district and station plans. Change in status and due date required. | June 25 - action ongoing | Behind Schedule
|  |  |  | PA2b. Produce guidance and resources for staff representing SYFR at community events | People Partner OD (EDI), EDI Advisor (JCSD) | 2024-04-01 | April 24 - completed with PACE toolkit and guidance. |  | April 25 - whilst the original task is complete, following evaluation from events further improvements to the accessibility of this information will be made in Q2 2025. | June 25 - action completed | Complete
|  |  |  | PA2c. Work with Business Intelligence & Joint Community Safety Department to develop a system to capture EDI related work. |  |  | April 24 - completed with PACE recording system. |  | Complete - but links to development work at OG5a. | June 25 - action completed | Complete
| 3. Utilise guidance, best practice and feedback to improve the way we deliver our services | Introduction of the NFCC Person Centred Framework |  | PA3a. Incorporate recommendations from NFCC tools, guidance and best practice into EDI related activity | People Partner OD (EDI), EDI Advisor (JCSD), Senior People Partner OD | Ongoing | Sept 24 - Person Centred Framework incorporated as part of review of Home Safety Fire Visits. | Feb 25 - PCF to be reviewed as part of ongoing Prevention Standard work. | April 25 - to be categorised as complete. | June 25 - action ongoing. New NFCC Anti-Racist Toolkit to be reviewed at JSG on 3rd July | On Schedule
| 4. Work with partners to provide learning and development opportunities for all | Learning and development opportunities are inclusive | FFTF IO11: All fire and rescue services will develop the management of data and digital capabilities to ensure evidence-based decision making. This will enable the measurement of benefits delivered through service activity, evaluation of the service and also support employee development. | PA4a. Facilitate joint working with blue light partners (including key dates in our calendar e.g. IWD) | People Partner OD (EDI), EDI Advisor (JCSD), Staff Groups | Ongoing | April 24 - for 2024 this will include International Women's Day and Black History Month. | Dec 24 - work ongoing to work in collaboration for key dates (IWD/BHM). Will be incorporated into EDI Calendar of Events for 2025. | April 25 - ongoing. | June 25 - action ongoing | On Schedule
| 5. Engage with national bodies and the NFCC to share best practice and consider examples | Best practice incorporated into EDI related activity |  | PA5a. Incorporate recommendations from NFCC tools, guidance and best practice into EDI related activity | People Partner OD (EDI), EDI Advisor (JCSD), Senior People Partner OD | Ongoing | May 24 - this work is ongoing. | Jan 25 - latest NFCC documents shared - Race Equality & Sexual Harassment Toolkits | April 25 - ongoing. | June 25 - action ongoing. New NFCC Anti-Racist Toolkit to be reviewed at JSG on 3rd July | On Schedule
COMMUNITIES | We will:
Put the interests of the public, community, and service users first by championing and valuing E&I Stand against all forms of discrimination, create equal opportunities, promote equality, foster good relations, and celebrate difference | 1. Consult when developing plans, policies etc. | Involvement at conception stages of plans and policies |  | CO1a. Develop community links | EDI Advisor (JCSD), District Teams, Partnership Manager | Ongoing | Aug 24 - this work is ongoing. | Feb 25 - Partnership Team have signed up partners from target groups to drive HFSV referrals | April 25 - ongoing. | June 25 - action ongoing | On Schedule
|  |  |  | CO1b. Utilise NFCC Tools e.g. Equality of Access | All |  | Aug 24 - this work is ongoing. |  | April 25 - ongoing. | June 25 - action ongoing | On Schedule
|  |  |  | CO1c. Refresh of post Home Fire Safety Visit (HFSV) survey, embedding elements of NFCC Person Centred Framework (PCF) data capture (HSC working group - CFRMIS upgrade) | EDI Advisor (JCSD), JCSD | 2024-09-01 | Aug 24 - this work is ongoing. | Feb 25 - NFCC Home Fire Safety Visit Evaluation Survey template now available | April 25 - ongoing. | June 25 - action ongoing | On Schedule
|  |  |  | CO1d. Introduce evaluation of our EDI practices | People Partner OD (EDI), EDI Advisor (JCSD), Projects, Education Advocate | 2025-01-01 | Aug 24 - this is incorporated into the PACE system. | Jan 25 - this is being developed as a priority for the PA role. MS Forms being used and some data now available. | April 25 - whilst classed as complete as at Jan 25 - the roll out of M365 this work will be expanded to improve quality and functionality of data gathered. | June 25 - action completed | Complete
|  |  |  | CO1e.Continue to develop our knowledge of cultural diversity within our communities to support the delivery of inclusive services | EDI Advisor (JCSD), Staff Groups | Ongoing | Aug 24 - this is included as an objective for our staff groups. | Feb 25 - Prevention PR should have one EDI objectives | April 25 - this is subject to the introduction of the updates in our PR system that will bring mandatory EDI objectives. | June 25 - update to PR system incorportating mandetory EDI objectives complete. To monitor outputs once data is available. | On Schedule
|  |  |  | CO1f. Identify and address potential barriers to our services to ensure they are culturally appropriate and inclusive | All |  | Aug 24 - this is included as an objective for our new PA role. | Feb 25 - CS WMs now have EDI references. BSL Interpreter engaged and used several times. Looking into Heat Alarms being connected up to HoH systems | April 25 - Meeting held with CS and Corp Comms to look at survey results on barriers to accessing SYFR services. EDI team to request results and discuss in next EDI meeting. | June 25 - report findings to be discussed at SLT prior to objectives for EDI team and others being communicated. | On Schedule
| 2. Reinforce our dedication to combatting racism in all its forms | Express our commitment to actively opposing racism and promoting racial justice Recommendations in Sheffield Race Equality Commission Report |  | CO2a. Review anti-racist statement, recognising the intersectionality of different forms of oppression and ensuring anti-racist stance addresses various forms of discrimination | People Partner OD (EDI), EDI Advisor (JCSD), Staff Groups | 2024-01-01 | Jan 24 - complete - for further review autumn 2024 | Jan 25 - Incorporated into work led by South Yorkshire Integrated Care Board (details in bulletin Issue 7 - 17 February 2025). Will require further work and a review of the target completion date. | April 25 - work ongoing with Anti Racist Group - learning / best practice to be shared with relevant teams. Will require a review of the due date and status. | June 25 - work ongoing. As identified above, work required to incorporate the NFCC Anti-Racism Toolkit and findings from the Anti Racist working group. | On Schedule
|  |  |  | CO2b. Review of REC | People Partner OD (EDI), EDI Advisor (JCSD), Staff Groups |  | Jan 24 - Monitored through attendance at Sheffield Equality Leads | Dec 24 - invitation to Doncaster Anti-racism recruitment process | April 25 - links to CO2a. | As per CO2a above. | On Schedule
|  |  |  | CO2c. Engage with minority ethnic owned businesses | EDI Advisor (JCSD), BFS | Ongoing | Jul 24 - will utilise PACE database and be part of work for new PA role once in post. | Ongoing | Ongoing | June 25 - action ongoing | On Schedule
| 3.Make better use of data to support local plans, performance measures and frontline work | Monitor data to plan resources and provide tools for wider and more effective community interaction | NFCC community related tools - Person Centred Framework? (Link to JCSD Actions?) | CO3a. Provide Community Handbooks and ensure that they are reviewed when new data becomes available | EDI Advisor (JCSD) | Ongoing | Aug 24 - work ongoing with corporate communication to produce in a more professional format and data team for content. Capture form created to be shared with districts during Oct 24. | Jan 25 - handbooks updated - spec sent to Corporate Comms provided to get professionally printed. | April 25 - review carried out and printer identified. Further work ongoing to review content to make more accessible. | June 25 - action ongoing | On Schedule
|  |  |  | CO3b. To be aware of developments within the third party Fire Risk Community Model |  |  | Aug 24 - ongoing | Feb 25 - Consultation carried out on CRMP in a variety of formats including Joint Staff Group and Staff Engagement Forum. | April 25 - ongoing | June 25 - action ongoing | On Schedule
|  |  |  | CO3c. Continue to develop guidance on EDI and Positive Action to enable relatability | People Partner OD (EDI), EDI Advisor (JCSD), PA & Engagement Officer |  | Jun 24 - completed with PACE toolkit and handbook but further comms required on a regular basis. | Jan 25 - comms (issue 7 - 17 February 2025) reminding re PACE & update at MM set for early Feb. | April 25 - comms Issue 6 - 10 February 2025, issue 7 - 17 February 2025, Issue 10 - 10 March 2025, Issue 12 - 24 March 2025, Issue 14 - 7 April 2025, Issue 16 - 22 April 2025. | June 25 - action ongoing | On Schedule
| 4. Prioritise leadership development to support the championing of EDI | Community Engagement at SLT level |  | CO4a. Monitor completion rates for EDI mandated training | People Partner OD (EDI), Senior People Partner OD, Business Intelligence | With Annual Report | Apr 24 - being carried out on regular basis and will be captured in the EDI Annual Report due to be approved in September 24. | Jan 25 - ongoing work with Business Intelligence to review and simplify collation of statistics relating to completion of EDI training. | April 25 - Ongoing | June 25 - some improvements made by Business Intelligence on reporting against LPIs. More work required to finalise this data so that it can be reviewed regularly. To consider impact of the move from LearnPro to MAKE e-learning platforms. | On Schedule
|  |  |  | CO4b. Capture evidence for EDI Annual Report | All |  | Apr 24 - comms sent to ask for evidence and reminder re use of PACE for this evidence. | As per 3c above. | April 25 - Ongoing | June 25 - action ongoing and is BAU on an annual basis. | Complete - move to BAU
| 5. Ensure positive action is translating into genuine recruitment outcomes | Change in our diversity profile |  | CO5a. Monitor impact of PA | People Partner OD (EDI), EDI Advisor (JCSD), Senior People Partner OD | Ongoing | Jul 24 - will form part of new PA role - links to AFI also. | Jan 25 - links into CO1d above. Updates made to application form for Wholetime & ON-Call as well as the fields in the Registrations of Interest spreadsheet to enable longer term monitoring of applicants and their involvement in our Positive Action work. Use of feedback and analysis of this to consider the impact of what we do. | April 25 - ongoing - links to CO1d. | June 25 - PA for wholetime recruitment June 25 now closed. Work underway for programme of PA for the remainder of 2025 and 2026 to incorporate evaulation and feedback. Will require longer term monitoring - process being developed currently. | On Schedule